## final
MRF | MRM validation and NTE obsevations | questions/clarifications | approach to closure
the MRF01 Documentation Issue and lack of evidence | reconciliation data through April 21, 2025, there was no evidence of reconciliation coverage through recent or at least June 30, 2025. appears to arise less from the actual analytical work and more from how the NTE evidence was compiled.but the submission to MRM contained data only through April 21, creating the perception that the effort ended prematurely. | was that procedural gap? was there lack of SME NTE Submission Review/Sign_Off? To avoid this occurence,should we Pre-submission quality review of NTE pack Evidence completeness checklist Final sign-off the package meets MRM documentation standards. The NTE submissiin included " explanation of mismatches but did not address if remediations are reflected in the NTE results | *Define NTE documentation standards per MRM expectations. *Define evidence completeness checklist and expectations on match rate, threshold and impact *Provide the evidence
the MRF01 “Inefficient Reconciliation” | The flagged GOV on Oct 2023 discrepancy lie outside the GVAR/SVAR windows. the MXN issue relates to a proxy already live in production (last year migration) not the Phase II dataset under review. The mismatches of GOV is within threadhold aggreed on | Should we set quantitative materiality thresholds for future NTEs? re-anchor expectations: ○ What was the match rate target for this NTE? ○ What tolerance thresholds were agreed (e.g., ±1bps)? Are we targeting a 100 % match rate, regardless of materiality or model impact? Are we expected to provide curve-by-curve justifications for every single date divergence ? regardless of GVAR/SVAR window? re-anchor expectations? | Those issues are idenfied in the TWC NTE .we should define reasonable expectations or there will implications of future NTEs At the time, the program was managing two parallel regulatory streams: (i) the VaR NTE, largely viewed as non-critical from a capital-impact perspective, and (ii) the EMR TWC reconciliation, which carried direct supervisory visibility and time-sensitive deliverables. if the new standard implies no NTE can be submitted until 100 % alignment is achieved across all time periods and systems, the outcome would be: • Persistent Yellow/Red NTE statuses, • Resource diversion from risk-impact work to forensic data matching • Delay of EMR/TWC deliverables
Should we pause all NTEs until we meet these new expectations of 100% reconciliation alignment, even if those differences are immaterial
is the approach of focusing on high-impact fixes and not chasing every minor difference not valid?
And if that’s the case, what’s the agreed-upon threshold or match rate we’re aiming for?
MRF02 Proxy issue and zero shifts | Zero shifts after May 2025 Per NTE documentation, NTE itself highlighted that there was a proxy mismatch : ○ EMR transition to MXN_FTII1D, and ○ Mars still using MXN_TII4W. and both MXN_FTII1D and MXN_TII4W migrated in phase 1 ( december last year) | if the same proxy was jointly approved by RA and MRO on Aug 2025, is that gaps Proxy ownership and synchronization between EMR and Mars? Is not the zero shifts are a symptom of the proxy not being updated at the source? And there is proxy oversight gaps between EMR and Mars? | define the ownership of proxy governance Once aggreed. as part of EMR TWC, we are loading data back to 2007, the fix would be to remove Mars proxy as part of the go-live
| Once curve is live and migrated, NTE sets the expectation that RFDM is pass through and proxy managemeent and aligment in done in EMR/MDSOR | Per NTE Can we confirm that RFDM is a pass-through and that MDSOR is the control point for proxy management and alignment
How do we formally define the ownership of proxy governance?

## Sheet1
I’ve consolidated our response to the recent MRM findings into a structured matrix to make the discussion factual and forward-looking.
’ve consolidated our response to the recent MRM findings into a structured matrix to make the discussion factual and forward-looking. The intent is not to debate the findings, but to clarify what actually happened, why the perception gap occurred, and how we prevent future recurrences without paralyzing ongoing workstreams.
MRF01 reflects a procedural gap, not a control failure and ambiguity between outcome of data recon and mrm validation and meeting deliverables
We need to re-anchor expectations around materiality and quantitative tolerance, not 100 % alignment.
Going forward, define quantitative reconciliation standards, materiality thresholds, and clear ownership for cross-system proxy and data alignment. A short joint governance workshop (MRM + RA + MRO + Market Data) is recommended to codify these standards and prevent recurrence in future NTEs and data migrations.
MRF01 is a procedural / documentation issue, not a validation failure. MRF02 is a proxy-governance timing gap, not a data-control breach. Going forward, define quantitative reconciliation standards, materiality thresholds, and clear ownership for cross-system proxy and data alignment. A short joint governance workshop (MRM + RA + MRO + Market Data) is recommended to codify these standards and prevent recurrence in future NTEs and data migrations.
The matrix also outlines a joint path forward: Define what “adequate evidence” means in quantitative terms (match-rate / bps tolerance). Establish ownership for proxy validation and cross-system consistency. Confirm that NTE submissions proceed based on material impact, with supplemental evidence allowed post-submission'